## Sheet1
WORKSHEET 5 - STATUS OF PAST PROJECTS
Jurisdiction | Mitigation Action |  | Hazard(s) Addressed |  | Responsible Party/Parties to Implement |  |  |  |  | Status - Check One |  |  |  | Status Details | Relevance - Check One |  | Relevance Details
|  | Previous Priority |  | Protecting which type of assets |  | Local planning mechanism identified to implement action | Initial Target Date for Completion | Estimated Cost | Funding Source(s) | Completed | Initiated but Not Completed | Ongoing Type of Activity | Not Initiated | If not completed, identify barriers to implementation (i.e., lack of political support, funding, staff availability, etc.) or explain why the action is an ongoing one (i.e., acquisition of hazard prone land for open space can be completed for a given parcel or group of parcels, but there may be many more opportunities in the community and so the activity may be carried forward) | Still Relevant - Carry Forward to Updated Mitigation Strategy | No Longer Relevant - Omit from Updated Mitigation Strategy | If you checked the box that the project is being carried forward to the updated mitigation strategy, describe if and how it has changed from the 2009 Plan. If you checked the box that the project is being omitted from the updated mitigation strategy, provide a brief explanation.
Ulster County | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Ulster County | 1.B. Ensure that local comprehensive plans incorporate natural disaster mitigation techniques by requiring a courtesy review of draft plans by the County Emergency Management Agency. | Medium | All hazard |  | EC/EM | Capital Improvement Program | 2009-2010 | $1.5 million | PDMP, FMAP, County Budget
Ulster County | 2.A. Expand and disseminate GIS and other hazard information on the internet. | Medium | All hazard |  | EC/EM | State Permits, Property Easements & Stormwater Mgmt. Plan | 2009-2010 | 500000 | PDMP, FMAP, County Budget
Ulster County | 4.D. Continue to implement best management practices for floodplain areas. | High | Flooding |  | EC/EM | State Permits & Property Acquisition | 2012-2013 | $6.5 million | PDMP, FMAP, State, County & Municipal Funds
Ulster County | 4.E. Identify and document repetitively flooded properties. Explore mitigation opportunities for repetitively flooded properties, and if necessary, carry out acquisition, relocation, elevation, and flood-proofing measures to protect these properties. | High | Flooding |  | EC/EM | State permits, OEM Planning | 2010 | $2.5 Million | PMDP, FMAP, Utilities & County Budget
Ulster County | 4.G Develop specific mitigation solutions for flood-prone road systems (roads, bridges, intersections, drainage, etc.) under the leadership of County DPW. | High | Flooding |  | DPW | Open Spac3 Plan | 2009-2013 | $15 Million | PDMP, FMAP, State, County, Municipalities & Non-Profits
Ulster County | 7.C. Construction of ice control structures such as booms, tension weirs and sloped-block barriers. | Low | Ice jams / flooding |  | EC/EM | Capital Improvement Program, State Permits, OEM Planning | 2009-2013 | $17.7 Million | PDMP, FMAP, State, County
Ulster County | 10.A. In consultation with NYSDEC Forest Protection & Fire Management and local forest rangers, develop mapping of wildland/urban interface areas. | Medium | Wildfires |  | EC/EM
Ulster County | 10.D. Endorse and promote prescribed burning for hazard reduction. | Medium | Wildfires |  | Fire Coord
Ulster County | 12.B. Review existing emergency response plans for enhancement opportunities: work with social support agencies, homeowners associations and general public to develop and implement monitoring and warning systems focused on vulnerable populations and provision of adequate shelter facilities. | High | All hazard |  | EC/EM
Ulster County | 2.E. Expand GIS via acquisition of HAZUS-MH to collect and develop more sophisticated hazard mapping. Use information to update plan. Ensure information will be available to the public and to relevant communities and agencies. | Medium | Earthquake, wind, and flood |  | EC/EM
Gardner, Town of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Gardner, Town of | Replace existing culvert with larger diam., re-do ditches, and repave sections of Old Ford, Lower Forest Glen, Bridge Creek, & Guildford Roads. Raising of some road beds may be required. | High | Flooding |  | Highway
Gardner, Town of | W/NYSDEC and 6 other towns that border the N. Shawangunk Ridge, develop a wildland/urban interface plan, incl. mapping, water sources develop & annually update mapping of wildland/ urban interface areas to include all potential alternative water sources for sources for drafting including swimming pools and identification of prescribed burn areas for hazard reduction. | High | Wildfires |  | Planning Board and Office of Emergency Management
Gardner, Town of | Continue the development of the Town’s Wetlands & Watercourse Law (220-35) to better manage storm water runoff. | Medium | Flooding |  | Environmental Conservation Comm. & Town Board
Gardner, Town of | Seek partnerships with the UC Red Cross and private and non-profit orgs. w/ large buildings to participate in a town emergency shelter program, e.g. St. Charles Borromeo & Gardiner Reformed Churches, Kiss My Face Cosmetics, and businesses in the Steve’s Lane business park. | Medium | Severe Storms |  | Town Board (Dir. of Emerg. Management)
Gardner, Town of | Rewrite Section 220-43 of the Town’s Zoning law, and as needed those sections (F,g, 1-7) of the Shaw. Ridge Protection Law (220-16) to provide for adequate emergency apparatus access and water supply/fire suppression, and which will be acceptable to the NYS DOS Codes Council. | High | Wildfires |  | Town Board with Code Enforcement Officer & Dir. of Emerg. Mgmt..
Gardner, Town of | Develop a plan and seek funding to retrofit the Town Hall with backup electric and communications systems so it can function as an EOC. | Medium | Severe storms, flooding, and wildfires |  | Town Board w/ Code Enforcement. Officer & Dir. of Emerg. Mgmt.
Gardner, Town of | Once the wildland/urban interface zone has been established and mapped, initiate the “Firewise” program in those areas to reduce the risk to structures and emerg. responders. | High | Wildfires |  | Two town fire departments w/ the Dir. of Emerg. Mgmt.
Gardner, Town of | Increase citizen awareness of natural hazards risks and mitigation steps they can take through public education and continued distribution of NYSEMO preparedness pamphlet series at public gatherings in the town | Medium | All |  | Dir. of Emerg. Mgmt.
Gardner, Town of | Encourage local businesses to create a preparedness plan for their facilities & distribute same to employees and the emerg. response agencies | Medium | All |  | Two town fire departments w/ the Dir. of Emerg. Mgmt.
Gardner, Town of | Partner with homeowners on Farmers Turnpike and Lower Forest Glen Road to develop a plan for retrofitting homes which have been subject to flooding | Low | Flooding |  | Planning Board, Code Enforcement Officer
Gardner, Town of | Obtain and Distribute at cost, or with a slight discount at Gardiner Day and other public events) NOAA weather alert radios w/a focus on e.g., day care centers churches, larger employers where there are a significant numbers of people and/or people who are part of vulnerable populations | High | Severe Storms, |  | Town Board (Dir. of Emerg. Management) With cooperation of local fire depts..
Gardner, Town of | Develop a plan and seek funding for backup electric power systems for those buildings which will become part of the Town’s emergency shelter system | Medium | All |  | Town Board and Planning Board
Hurley, Town of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Hurley, Town of | Channel improvement - Esopus Creek through Town of Hurley | High | Flood |  | Town Board, Ulster County, DEC, Army Corps of Engineers
Hurley, Town of | Drainage improvement - redo culverts and ditches in the Bristol Hill development | Medium | Flood |  | Town Board, Highway Department
Hurley, Town of | Drainage improvement - redo culverts and ditches along Broad and Birch Street | Medium | Flood |  | Town Board, Highway Department
Hurley, Town of | Natural resource protection - acquire property on Brink's Lane for town park | Medium | Flood |  | Town Board
Hurley, Town of | Preventative measure - adjust building and zoning code to increase wind capacity for new structures | Low | High wind/ Hurricane |  | Town Board, Building Inspector, Zoning Board
Kingston, City of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Kingston, City of | Drainage improvements on 3 sections of Linderman Ave (Tannery Brook). Replace culvert, stabilize stream bank and work with Twin Ponds development to address issues and mitigate flooding downstream from the development. | High | Flooding, Road erosion |  | Public Works
Kingston, City of | Replace existing stormwater pipe and culvert along the Jacobs Valley storm sewer line near Wiltwyck Cemetery. Alleviate flooding at the Broadway underpass, Susan Street area, that occurs during any significant rainfall | High | Flooding, eliminate street closure, improve evacuation route and emergency response |  | City Engineer, Public Works
Kingston, City of | Drainage and Storm Sewer improvements in the Hurley Ave, Fairview Ave, Millers Lane area to alleviate street and home flooding | High | Flooding |  | City Engineer
Kingston, City of | Replace four sections of culvert Main St., Mt View, Lucas Ave area to Esopus Creek to eliminate flooding of homes and business district | High | Flooding |  | City Engineer, Public Works
Kingston, City of | Stream stabilization at Twaffskill Creek adjacent to Wilbur Ave/ Chapel St. to prevent reoccurrence of erosion that causes road to slide into creek and threatens water and sewer lines | High | Erosion, Road Collapse |  | City Engineer
Kingston, Town of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Kingston, Town of | Mitigate stream corridor obstructions in the Sawkill Creek by stream corridor restoration | Medium | Flooding |  | Flood Coordinator and Highway Department
Kingston, Town of | Mitigate local road flooding on Sawkill Road with Storm Water Management Plan | High | Flooding |  | Flood Coordinator and Highway Department
Kingston, Town of | Construct ring levee or floodwall system around Town Hall, Highway Building, and Fire House | High | Flooding |  | Flood Coordinator and Highway Department
Lloyd, Town of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Lloyd, Town of | Dredge and clean Shantz’s Pond on the south branch of the Twaalfskill to increase storm water detention volume so as to reduce flooding along and over roadways in the area of the Hamlet of Highland and along River Road. | 1 | Flooding of roadways and structures |  | Highway Dept. in Conjunction with Town Engineer
Lloyd, Town of | Dredge and clean ponds (Pratt Mill Pond and others) along the North Branch Twaalfskill to increase storm water detention volume so as to reduce flooding along and over roadways in the area of the Hamlet of Highland and along River Road. | 2 | Flooding of roadways and structures |  | Highway Dept. in Conjunction with Town Engineer
Lloyd, Town of | Dredge and clean unnamed stream along Mile Hill Road and construct a detention pond on the Alfono property to reduce flooding and washouts along Mile Hill Road, to protect regional high pressure gas main serving Dutchess County and to protect major water mains serving the Hamlet of Highland. | 3 | Flooding of roadways, structures, and critical utility lines |  | Highway Dept. in Conjunction with Town Engineer
Lloyd, Town of | Dredge and remove the sediment in both branches of the Twaalfskill as well as removal of the alluvial deposit at the Twaalfskill outlet in the Hudson River to reduce flooding of adjoining properties. | 4 | Flooding of roadways and structures |  | Highway Dept. in Conjunction with Town Engineer
Marbletown, Town of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Marbletown, Town of | Localized minor flood reduction projects (upgrading of drainage systems in key, flood prone areas | High | Flooding |  | Highway
Marbletown, Town of | Infrastructure protection measures grading, drainage upgrading, planting, use of geo- fabrics at recycling and community centers, town hall, highway facility, town park. | Medium | Flooding, Erosion/Sed. Control |  | Highway
Marbletown, Town of | Channel maintenance, periodic cleaning out of drainage channels, plus continuous inspections. | High | Flooding |  | Highway
Marbletown, Town of | Enhanced floodplain development regulations and zoning | Medium | Flooding |  | Town Board and Planning
Marbletown, Town of | Public awareness and information, including workshops, literature, dedicated web page | High | All |  | Supervisor and Environment Comm.
Marlborough, Town of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Marlborough, Town of | Develop fire hazard severity overlay zone | 1 | Wildfires |  | Town Planning and GIS
Marlborough, Town of | Institute education requirements for planning board in mitigation methods for subdivision/site plan review | 2 | Wildfires |  | Town Planning
Marlborough, Town of | Signage to identify fire hazard risks | 3 | Wildfires |  | Town Board / Building Department
Rosendale, Town of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Rosendale, Town of | Various locations in the Town of Rosendale including but not limited to Rondout Creek, Wallkilll River Coxingkill Creek, Cottekill Brook Dewitt Mill Stream, unnamed stream adjacent to River Road and River Road extension, Underground storm water drainage in High Falls Park, Tillson Estates and Clark Estates have been identified. Mitigation will include updating Comprehensive plan, revising zoning codes so issues will be addressed during site plan review, sub division approval, Rosendale Highway Department replacing storm water basins and culverts, and US Army Corps of Engineers updating flood control engineering and mapping. Also public outreach and education, updating building codes, bank stabilization, erosion control and Emergency management coordination with Highway Department, Fire Departments, Police Departments, and EMS | High | Flood |  | Town Board, Planning Board, Zoning Board, Town Highway Department, Building Department
Rosendale, Town of | Various locations in the Town of Rosendale including but not limited to Joppenburgh Mountain, All Forming Minning areas, NYS RT 213 corridor from Lawrenceville Bridge to Keator Ave Bridge, Woodland Drive at terminus, Mountain Road, Shawangunk Ridge, Creek Locks Road, Bruceville Road, School lane, Spring Street, NYS Route 32 have been identified. Mitigation will include, bank stabilization, erosion control, culverts and ditches, removal of hazards through blasting and coordinating with Federal, State and County agencies to share mitigation tasks management Coordination with Highway Department, Fire Departments, Police Departments, and EMS | High | Landslides |  | NYSDOT, Ulster County Highway Department, and Town Highway Department
Rosendale, Town of | Various locations in the Town of Rosendale including but not limited to Sturgeon Pool, Iron Mountain Dam, Mountain Road Dam Adjacent to Binnewatter Road have been identified. Mitigation will include coordinating with emergency action plans with Dam owners, requiring engineering reports and inspection, repair and maintenance programs or materials to property owners. | High | Dam Failure |  | Town Board
Rosendale, Town of | Various locations in the Town of Rosendale including but not limited to Joppenbugh Mountain, Shawangunk Ridge, Mohonk Persevere, Bloomington Forest, Binnewater Forest, Burnt Swamp Preserve have been identified. Mitigation will include creating fire lanes and bermes in the unbroken forested areas, using controlled burns, providing public education programs and materials to property owners. | Medium | Wildfires |  | Town Board
Rosendale, Town of | Mitigation will include coordinating with Federal, State and County agencies including the local jurisdiction to implement a readiness plan to address the various hazards, support local highway department with training, equipment and technical information also offer public education and materials. Set up a information page on our Town web site for the public to access and monitor. | High | Nor'easter, Tornadoes, Winter Storms, Hurricanes, and Earthquakes |  | Town Board
Rosendale, Town of | The Former Wallkill Valley Railroad trestle and a communications tower located in Maple have been identified as being vulnerable to severe categories cited in the Plan, including extreme wind storm, tornadoes, lightning, winter storm and earthquake. | Low | Vulnerable Structures |  | Town Board
Saugerties, Town of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Saugerties, Town of | Increase culvert diameter size in Barclay Heights, Mt. Marion, Blue Mountain Park, Village of Saugerties. | High | Flood |  | DOT Local Government
Saugerties, Town of | Barclay Heights has many cul-de-sacs, most property is held up, these areas are key drainage areas for runoff; however, years of debris have accumulated and need to be removed. | High | Flood |  | Town DOT
Saugerties, Town of | Raise State Route 9W in Glenerie, a major evacuation route for the Township. This stretch of highway is located next to the Esopus Creek and has experienced flooding. | Medium | Flood |  | State DOT
Saugerties, Town of | Designate more protected wetland areas within the township, George Sickle Rd., and the area surrounding the Plattekill Creek. | High | Flood (50yr) |  | Town Government, County Legislature
Shandaken, Town of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Shandaken, Town of | Relocation of town garage and town hall, or elevate above floodplain | Medium | Flood |  | Town
Shandaken, Town of | Repair retaining wall on Woodland Valley, 3 places | High | Flood |  | Highway
Shandaken, Town of | Repair retaining wall on Miller Road | Medium | Flood |  | Highway
Shandaken, Town of | Flood control wall on Brown Road | High | Flood |  | Highway
Shandaken, Town of | Flood control for the Town of Phoenicia | High | Flood |  | Highway
Shawangunk, Town of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Shawangunk, Town of | Educate residents on disaster preparedness, to prevent loss of life and property | Medium | All |  | Town Board
Shawangunk, Town of | Walkill Hamlet flooding | Medium | Flooding |  | Town Board
Shawangunk, Town of | Borden Dam Failure | Medium | Flooding |  | Town Board
Ulster, Town of | Provide a General Overview of How Local Priorities May Have Changed Since the Last Version of the Plan:
Ulster, Town of | Mitigate damage to homes on Orlando Street either by purchase and demolition or retrofitting by raising the homes | High | Flooding |  | Flood Coordinator, Highway, and Building Departments
Ulster, Town of | Mitigate damage to homes on Sandy Road either by purchase and demolition or retrofitting by raising the homes | High | Flooding |  | Flood Coordinator, Highway, and Building Departments
Ulster, Town of | Mitigate damage to homes on Lower Katrine Lane either by purchase and demolition or retrofitting by raising the homes | High | Flooding |  | Flood Coordinator, Highway, and Building Departments
Ulster, Town of | Mitigate soil erosion and undercutting of the Esopus Creek banks that threaten homes on Brigham Lane by vegetation management and soil stabilization | High | Erosion |  | Flood Coordinator, Highway, and Building Departments
Ulster, Town of | Construct ring levee or floodwall system around Town of Ulster Waste Water Treatment Plant off Dogwood Lane | High | Flooding |  | Flood Coordinator, Highway, and Building Departments
Ulster, Town of | Construct ring levee or floodwall system around Town of Ulster Water Treatment Plant off Fording Place Road | High | Flooding |  | Flood Coordinator, Highway, and Building Departments
Ulster, Town of | Mitigate stream obstructions in the Esopus Creek by stream corridor restoration | High | Flooding |  | Flood Coordinator, Highway, and Building Departments